## Project Plan
Iteration 1, 4 wks 3/19/18 - 4/16/18 | Iteration 2, 4 wks 4/17/18 - 5/15/18 | Iteration 3, 4 wks 5/16/18 - 6/13/18
UC1: Search for Programs points: 3 Priority: 1 Depends on: None | UC3: Submit Online Application Points: 2 Priority: 3 Depends on: None | UC5: Logout Points: 3 Priority: 4 Depends on: UC4
UC2: Display Program Detail Points: 4 Priority: 1 Depends on: UC1 | UC4: Login Points: 2 Priority: 4 Depends on: None | UC6: Edit Online Application Points: 3 Priority: 2 Depends on: UC3
UC7: Approve Course Equivalency Form Points: 2 Priority: 2 Depends on: None | UC8: Submit Recommendation Points: 5 Priority: 3 Depends on: None | UC9: Approve Course Equivalency Points: 3 Priority: 2 Depends on: None

## Risk Management
Risks | Resolution Measures
Personnel Shortfalls | User job recruiter to hire top talent and prevent issues by paying competitively
Unrealistic schedules and budgets | Scrub the requirements to trim down on possible excess development cost and use schedule estimation to ensure the project does not go past schedule.
Gold-plating | A cost-benefit analysis will be performed to mitigate unnecessary features.
Continuing stream of requirements changes | A high change threshold will be implemented to deal with additional changes and incremental development will be used to allow for changes during development.
Shortfalls in externally furnished components | Hardware will be benchmarked and inspected to ensure performance standards are met, compatibility will be tested thoroughly.
Deliverables are produced at each stage
Software configuration items can affect each other

## Sheet1
baseline | SCI's
Planning Baseline | - Project Management - Configuration Management - Risk Management
Requirements Baseline | - Update to planning baseline - domain model refinement - validation test plan - preliminary user's manual
Design Baseline | - software design document - integration test plan
Implementation Baseline | - unit test cases - source code lists - unit test reports
Integration Baseline | - integration test cases - test report
Validation Baseline | - validation test cases - validation test reports - installation manual - user's manual - user's guide
Planning Phase | Project Management
Configuration Management
Risk Management
Iteration 1 | Planning
Requirements
Design
Implementation
Integration Validation
Iteration 2 | Planning
Requirements
Design
Implementation
Integration Validation
Iteration 3 | Planning
Requirements
Design
Implementation
Integration Validation
Iteration 1 | Planning | requirements
Domain Model
Program Search Expanded Use Case Diagram
Use Case Diagrams
Requirement-use case traceability matrix
Use case delivery schedule
Draft Architectural design
| Requirements | update to planning baseline items
domain model or its refinement
validation test plan
preliminary user's manual
| Design | software design document
integration test plan
| Implementation | unit test cases
source code lists
unit test reports
| Integration | use case based integration test cases
test reports
| Validation | validation test cases
validation test reports
installation manual
as-built user's manual
user's guide
Iteration 2 | Planning | requirements
Domain Model
Use Cases
Use Case Diagrams
Requirement-use case traceability matrix
Use case delivery schedule
Draft Architectural design
| Requirements | update to planning baseline items
domain model or its refinement
validation test plan
preliminary user's manual
| Design | software design document
integration test plan
| Implementation | unit test cases
source code lists
unit test reports
| Integration | use case based integration test cases
test reports
| Validation | validation test cases
validation test reports
installation manual
as-built user's manual
user's guide
Iteration 3 | Planning | requirements
Domain Model
Use Cases
Use Case Diagrams
Requirement-use case traceability matrix
Use case delivery schedule
Draft Architectural design
| Requirements | update to planning baseline items
domain model or its refinement
validation test plan
preliminary user's manual
| Design | software design document
integration test plan
| Implementation | unit test cases
source code lists
unit test reports
| Integration | use case based integration test cases
test reports
| Validation | validation test cases
validation test reports
installation manual
as-built user's manual
user's guide